## Audit Summary
Standard | Control / Item | Status | Risk (if applicable) | Notes
GDPR | Right to erasure (partial operational path exists): user deletion workflow removes user record plus related tokens/requests in course-forge-backend/src/main/java/com/mundrisoft/courseforge/service/UserService.java (deleteUser). | Implemented |  | GDPR Implemented control
GDPR | Personal data collection is explicit through DTO contracts with validation annotations (e.g., UserRequestDto, UpdateBillingContactRequestDto, SetPasswordDto) under course-forge-backend/src/main/java/com/mundrisoft/courseforge/dto. | Implemented |  | GDPR Implemented control
GDPR | Some retention logic exists for temporary/operational files and editor sessions via scheduled cleanup in FileCleanupService and SCORM session cleanup services. | Implemented |  | GDPR Implemented control
GDPR | Data portability is implemented for course/package exports (course-forge-backend/src/main/java/com/mundrisoft/courseforge/export/controller/CourseExportController.java) but not clearly for subject-level personal data export. | Partial |  | GDPR Partial control
GDPR | Data minimization is inconsistent: DTO validation exists, but broad collection of contact/profile fields is present across multiple DTOs without code-level purpose/necessity enforcement. | Partial |  | GDPR Partial control
GDPR | Purpose limitation is partly implicit in service/controller flows, but there is no explicit code-level tagging/enforcement of processing purposes. | Partial |  | GDPR Partial control
GDPR | Data inventory and access mapping are partially covered through DTO/entity/service usage, but there is no centralized record of what personal data is held, where stored, and who can access each category. | Partial |  | GDPR Partial control
GDPR | Data retention exists in isolated flows (file/session cleanup, user deletion path) but not as a complete GDPR retention schedule per data category. | Partial |  | GDPR Partial control
GDPR | Security controls are partially implemented (JWT auth, BCrypt, selective audit logging), but GDPR-specific safeguards such as pseudonymization/anonymization policy enforcement are not uniformly applied. | Partial |  | GDPR Partial control
GDPR | Email consent-related mechanics exist in auth/verification flows, but explicit GDPR-grade marketing consent state and unsubscribe lifecycle governance are not fully modeled in current backend artifacts. | Partial |  | GDPR Partial control
GDPR | Consent tracking controls are not evidenced in code (no clear consent entity/ledger/versioned consent capture flow found). | Missing |  | GDPR Missing control
GDPR | Comprehensive GDPR subject-access/export endpoint for user/account/billing activity data is not evidenced. | Missing |  | GDPR Missing control
GDPR | Centralized retention/deletion policy engine for persisted PII across all entities is not evidenced. | Missing |  | GDPR Missing control
GDPR | No explicit minors/age-threshold (under 16) collection and parental consent control flow is evidenced in backend privacy controls. | Missing |  | GDPR Missing control
GDPR | No dedicated record of processing activities (RoPA-style) is evidenced for GDPR accountability requirements. | Missing |  | GDPR Missing control
GDPR | No explicit third-party processor governance register (processor list, purpose, DPA status, controls) is evidenced in code-level compliance assets. | Missing |  | GDPR Missing control
GDPR | No international transfer control register (EEA to non-EEA transfer basis, safeguards, risk assessment references) is evidenced in compliance artifacts. | Missing |  | GDPR Missing control
GDPR | Cookie-consent management backend support (opt-in categories, persistent opt-out, consent recall/change history) is not evidenced in current backend scope. | Missing |  | GDPR Missing control
GDPR | Form-level consent metadata capture (privacy notice acceptance, correspondence opt-in choices, timestamped consent proof) is not comprehensively modeled across data collection endpoints. | Missing |  | GDPR Missing control
GDPR | Breach-response readiness controls (72-hour supervisory notification workflow, affected-user notification workflow, incident evidence package) are not implemented as structured backend process modules. | Missing |  | GDPR Missing control
GDPR | Privacy policy version acceptance tracking (which user accepted which policy version and when) is not evidenced as a dedicated compliance control. | Missing |  | GDPR Missing control
SOC2 | Authentication token validation exists via JWT utility and interceptor (JwtUtil, JwtInterceptor, WebConfig). | Implemented |  | SOC2 Implemented control
SOC2 | Password hashing with BCrypt is configured and used (SecurityConfig password encoder; usage in auth/user service flows). | Implemented |  | SOC2 Implemented control
SOC2 | Audit event mechanism exists (UserAccessEvent + AuditTrailListener) and at least one controller publishes audit events (UserController). | Implemented |  | SOC2 Implemented control
SOC2 | Basic health monitoring exposure exists through Actuator health endpoint in application.properties and application-prod.properties. | Implemented |  | SOC2 Implemented control
SOC2 | Access control is split/inconsistent: Spring Security filter chains permit all (SecurityConfig), while auth enforcement is mainly custom interceptor/manual checks. | Partial |  | SOC2 Partial control
SOC2 | RBAC exists but is uneven: isolated @PreAuthorize and manual role checks in controllers/services, not uniformly enforced through a centralized policy model. | Partial |  | SOC2 Partial control
SOC2 | Audit logging coverage appears limited to selected actions; no repository-wide evidence of comprehensive security/audit trail for all critical data changes. | Partial |  | SOC2 Partial control
SOC2 | Evidence of Redis caching controls is missing because Redis integration itself is not present (no Redis client/config usage found). | Missing |  | SOC2 Missing control
SOC2 | Evidence of Riak storage controls is missing because Riak integration itself is not present (no Riak usage found). | Missing |  | SOC2 Missing control
SOC2 | Centralized security monitoring instrumentation (e.g., broad metrics/tracing/alert hooks) is not clearly evidenced beyond health endpoint and application logs. | Missing |  | SOC2 Missing control
ISO27001 | Password protection control is implemented with BCrypt (SecurityConfig + auth/user service encoding calls). | Implemented |  | ISO27001 Implemented control
ISO27001 | JWT signatures are cryptographically validated using HS256 in JwtUtil. | Implemented |  | ISO27001 Implemented control
ISO27001 | TLS usage is configured for SMTP (smtp.ssl.enabled=true, TLS protocol settings in application property files). | Implemented |  | ISO27001 Implemented control
ISO27001 | Encryption practice is mixed: strong password hashing exists, but symmetric utility uses hardcoded key and AES/ECB mode in EncryptionUtil. | Partial |  | ISO27001 Partial control
ISO27001 | Secure configuration is partial: production profile reduces verbosity and limits actuator exposure, but insecure/unsafe defaults remain in config set (e.g., DB useSSL=false, ddl-auto=update). | Partial |  | ISO27001 Partial control
ISO27001 | Risk controls are partially documented in code comments and selective checks, but not uniformly codified across all sensitive flows. | Partial |  | ISO27001 Partial control
ISO27001 | Secrets management is not implemented in a compliant code pattern: numerous secrets/credentials/API keys are directly present in application.properties and application-prod.properties. | Missing |  | ISO27001 Missing control
ISO27001 | No code evidence of key rotation/revocation lifecycle for JWT secrets/API secrets. | Missing |  | ISO27001 Missing control
ISO27001 | No code evidence of systematic field-level encryption policy for sensitive persisted business/PII data. | Missing |  | ISO27001 Missing control
GLOBAL | Risk Item | Risk | Hardcoded secrets and credentials in config files (spring.datasource.password, jwt.secret, OpenAI keys, SMTP password, ZeptoMail key, Stripe keys) create credential exposure and compromise risk. | Cross-standard risk
GLOBAL | Risk Item | Risk | Authorization model risk: SecurityConfig permits all requests at filter-chain level, with enforcement moved to custom interceptor/manual checks, increasing bypass/misconfiguration risk. | Cross-standard risk
GLOBAL | Risk Item | Risk | Potential sensitive-data logging risk: request-associated values (e.g., imageUrl, sessionId, search criteria) and exception message propagation appear in controller logging/response paths. | Cross-standard risk
GLOBAL | Risk Item | Risk | Cryptographic weakness risk from EncryptionUtil hardcoded AES key and AES/ECB/PKCS5Padding usage. | Cross-standard risk
GLOBAL | Risk Item | Risk | Data subject rights coverage risk: deletion exists for user path, but comprehensive personal-data portability and consent lifecycle evidence is not present. | Cross-standard risk
GLOBAL | Risk Item | Risk | Assurance gap risk for cache/NoSQL controls because Redis/Riak control implementation is absent in code. | Cross-standard risk
GLOBAL | Risk Item | Risk | GDPR governance risk: missing centralized processor/international transfer controls can expose the organization to cross-border compliance violations. | Cross-standard risk
GLOBAL | Risk Item | Risk | Consent evidence risk: absence of structured cookie/form/privacy-policy consent logs may weaken legal defensibility during audits or complaints. | Cross-standard risk
GLOBAL | Risk Item | Risk | Incident response risk: without breach workflow orchestration and notification tracking, 72-hour GDPR notification obligations may be missed. | Cross-standard risk
GLOBAL | Requires infrastructure or policy validation: whether repository secrets are overridden by runtime secret managers and not used in deployed environments. | Requires Validation |  | Requires infrastructure or policy validation
GLOBAL | Requires infrastructure or policy validation: production network controls around actuator and API endpoints (private access, WAF/API gateway rules). | Requires Validation |  | Requires infrastructure or policy validation
GLOBAL | Requires infrastructure or policy validation: log pipeline encryption, retention, RBAC, redaction, and SIEM forwarding controls. | Requires Validation |  | Requires infrastructure or policy validation
GLOBAL | Requires infrastructure or policy validation: database/storage encryption at rest, backup encryption, and KMS/HSM governance. | Requires Validation |  | Requires infrastructure or policy validation
GLOBAL | Requires infrastructure or policy validation: formal consent governance/process may exist outside application code (legal/policy/workflow systems). | Requires Validation |  | Requires infrastructure or policy validation
GLOBAL | Requires infrastructure or policy validation: incident monitoring/alerting stack may exist outside this repository. | Requires Validation |  | Requires infrastructure or policy validation
GLOBAL | Requires infrastructure or policy validation: whether a separate legal/compliance system maintains RoPA, processor DPAs, and transfer impact assessments outside this repository. | Requires Validation |  | Requires infrastructure or policy validation
GLOBAL | Requires infrastructure or policy validation: whether frontend/web platform already implements GDPR cookie banner mechanics with backend consent persistence not represented here. | Requires Validation |  | Requires infrastructure or policy validation
GLOBAL | Requires infrastructure or policy validation: whether formal incident response runbooks and regulatory notification workflows are implemented in SOC/ITSM tools external to codebase. | Requires Validation |  | Requires infrastructure or policy validation
Legend
Implemented | Control implemented
Partial | Control partially implemented
Missing | Control missing
Risk | Risk statement row
Requires Validation | Needs infra/policy validation

## Design Plan
Issue | Root Cause | Solution Summary | Code Changes (short) | Data Changes | Security Improvements | Compliance Mapping
GDPR Partial: Data portability only covers course/package exports, not subject-level personal data export | Export implementation is domain-specific (CourseExportController/export services) and there is no unified data-subject aggregation service spanning user, billing, auth, and usage repositories. | Add a GDPR portability module with DataPortabilityController (GET /v1/privacy/me/export), DataPortabilityService, and repository adapters. Use async export orchestration (job table + signed download URL) and DTO-based s… | Controller: new DataPortabilityController secured with @PreAuthorize("isAuthenticated()"); Service: DataPortabilityService.buildExport(userId) pulls from UserRepository, BillingContactRepository, ApiUsageRepository, etc… | DB: add privacy_export_jobs (id, user_id, status, expires_at, checksum); Redis: cache export job progress with TTL (e.g., 24h) to avoid polling DB hot paths; Riak: optional object bucket for large export artifact chunks… | Require fresh JWT + optional step-up check before export generation, sign download links, enforce one-user access boundary, and audit each export request/result. | GDPR Art. 20 (Data Portability), SOC2 CC6/CC7 (access and processing control), ISO 27001 A.5/A.8 (information access and handling)
GDPR Partial: Data minimization is inconsistent across DTOs | DTOs validate format but not necessity; controllers accept broad payloads without purpose-scoped field policies, and services do not enforce context-aware field whitelists. | Introduce purpose-scoped request models and validation groups (@Validated(CreateProfile.class) etc.). Add a DataMinimizationPolicyService enforcing allowed fields per endpoint purpose and role. | Controller: replace generic DTOs with purpose-specific DTOs (BillingContactUpdateDto, TenantOnboardingDto, etc.); Service: add validateAllowedFields(purpose, payload) before persistence; Config: add custom ConstraintVal… | DB: no mandatory schema change, but optionally split rarely used sensitive attributes into separate table with strict access path; Redis: cache minimization policy map keyed by endpoint+role with short TTL. | Reduce attack surface from over-posting/mass assignment, enforce strict JSON property binding (FAIL_ON_UNKNOWN_PROPERTIES=true for sensitive endpoints), and reject unnecessary PII ingestion. | GDPR Art. 5(1)(c) Data Minimization, SOC2 CC3/CC6, ISO 27001 A.8 (information classification/handling)
GDPR Partial: Purpose limitation is implicit, not explicit/enforced | Processing purpose is embedded in business logic and not represented as a first-class policy attribute in API/service layers. | Add purpose-tag propagation from API to service (ProcessingPurpose enum). Enforce via AOP interceptor (@RequiresPurpose) and policy matrix service. | Controller: annotate endpoints with @RequiresPurpose(Purpose.BILLING_CONTACT_UPDATE); Service: accept ProcessingContext with purpose and actor; Aspect: block unauthorized purpose/data combinations before method executio… | DB: add processing_purpose and legal_basis columns to audit records; Redis: cache purpose policy matrix and invalidate on policy change; Riak: include purpose metadata in object headers for immutable audit context. | Centralized purpose checks prevent function creep, improve traceability, and harden against unauthorized secondary use of collected data. | GDPR Art. 5(1)(b) Purpose Limitation, SOC2 CC2/CC7, ISO 27001 A.5/A.8
GDPR Missing: Consent tracking ledger/versioning not implemented | No consent domain model, no evented consent capture endpoint, and no versioned policy references tied to user actions. | Implement ConsentController + ConsentService with versioned consent records (policy_version, purpose, status, timestamp, source_ip, user_agent). Use append-only consent events and immutable hash chain for integrity. | Controller: POST /v1/privacy/consents and GET /v1/privacy/consents; Service: recordConsent(command) and withdrawConsent(...); DAO: ConsentRepository; add @PreAuthorize("isAuthenticated()") and service-level ownership ch… | DB: new user_consents and consent_events tables with unique index (user_id,purpose,policy_version); Redis: cache current consent state per user/purpose TTL 15m for fast policy checks; Riak: store consent event snapshots… | Sign consent payload digest, enforce write-once event records, and include consent status check in business flows before processing optional personal data. | GDPR Art. 6/7 (lawful basis and consent), SOC2 CC6/CC8, ISO 27001 A.5/A.8/A.12
GDPR Missing: Comprehensive subject-access endpoint not implemented | No DSAR orchestration layer; data access remains fragmented by bounded contexts and endpoint ownership. | Add DSAR APIs (/v1/privacy/me/access-report) producing machine-readable + human-readable reports. Orchestrate with service fan-out and standardized mappers. | Controller: DataSubjectAccessController; Service: DsarAggregationService; DAO: repository adapters returning scoped projections; add request throttling and asynchronous job processing. | DB: dsar_requests table for status, SLA clock, and fulfillment logs; Redis: DSAR workflow state TTL and idempotency keys; Riak: archive generated reports with retention policy metadata. | Strong requester verification, request anti-replay, per-user scoping, signed report artifacts, and complete DSAR audit trail. | GDPR Art. 15 (Right of Access), SOC2 CC6/CC7, ISO 27001 A.5/A.8
GDPR Missing: Centralized retention/deletion policy engine for PII | Retention is implemented in isolated services (file/session cleanup) without global policy registry and entity-level enforcement. | Implement retention policy engine with declarative rules (RetentionPolicy), scheduled executor, and deletion/anonymization handlers per entity type. | Config: RetentionPolicyConfig loads policy from DB/YAML; Service: RetentionEngineService.run(); DAO: retention queries per repository; add @Scheduled orchestrator + dead-letter handling. | DB: retention_policies and retention_execution_log; Redis: lock keys (SETNX) for singleton scheduler and per-batch checkpoints TTL; Riak: use bucket-level lifecycle tags and delete markers. | Deterministic expiry handling, reduced stale-PII risk, tamper-evident execution logs, and controlled purge workflows with dual-control for sensitive domains. | GDPR Art. 5(1)(e) Storage Limitation & Art. 17, SOC2 CC8, ISO 27001 A.8/A.12
SOC2 Partial: Access control split between permitAll filter chain and custom interceptor/manual checks | Spring Security is not the single enforcement point; authorization logic is duplicated in interceptors/controllers, creating policy drift. | Move to SecurityFilterChain-first enforcement: deny-by-default, JWT auth filter (OncePerRequestFilter), and standardized exception handling (AuthenticationEntryPoint, AccessDeniedHandler). | Config: replace .anyRequest().permitAll() with explicit permit list + .anyRequest().authenticated(); Security: add JwtAuthenticationFilter populating SecurityContext; Controller/Service: remove manual bearer parsing and… | Redis: maintain token jti blacklist/session-state cache TTL to support revocation and logout; DB optional: revoked_tokens for durable revocation. | Single policy plane, fewer bypass paths, consistent 401/403 behavior, and stricter endpoint hardening. | SOC2 CC6 (logical access), ISO 27001 A.5/A.8, GDPR Art. 32
SOC2 Partial: RBAC exists but is uneven and not centralized | Role checks are mixed (@PreAuthorize in few places, manual role parsing elsewhere) and no unified authorization policy service exists. | Enable method security globally and standardize role/attribute checks with SpEL policies + custom PermissionEvaluator. | Config: @EnableMethodSecurity; Service/Controller: annotate privileged operations (@PreAuthorize("hasRole('SUPER_ADMIN') or @perm.canAccessWorkspace(authentication,#workspaceId)")); add PermissionEvaluator and workspace… | DB: normalize role-permission matrix tables (roles, permissions, role_permissions); Redis: cache permission graph by role with cache invalidation on admin changes. | Consistent least-privilege authorization, context-aware access checks, and reduction of ad-hoc role parsing bugs. | SOC2 CC6.1/CC6.2, ISO 27001 A.5 (access control), GDPR Art. 32
SOC2 Partial: Audit logging coverage is limited to selected actions | Audit event publication is manual and sparse; no cross-cutting mechanism captures high-risk CRUD/auth/privilege actions consistently. | Implement audit as cross-cutting concern using AOP (@Auditable) plus security event listeners and persistence-backed audit store. | Create @Auditable(action="..."); Aspect captures actor, target, before/after hash, request ID; Service layer annotates critical methods; add async AuditWriter with SLF4J structured JSON output. | DB: audit_log table partitioned by date; Redis: short-term stream/buffer for burst writes; Riak: immutable archive bucket for long-retention audit records. | Tamper-resistant logs (hash chain/signature), full traceability for sensitive operations, and easier incident reconstruction. | SOC2 CC7/CC8, ISO 27001 A.12 (logging/monitoring), GDPR Art. 30/32
SOC2 Missing: Redis caching controls absent because Redis integration is absent | No cache architecture was implemented for security-sensitive state (revocation, rate limiting, ephemeral risk controls). | Add Redis with Spring Data Redis for token revocation, rate limiting, and ephemeral policy caches. Define cache namespaces and security TTL standards. | Config: RedisConfig (LettuceConnectionFactory, RedisTemplate, cache manager); Security: TokenRevocationService using jti keys; Filter: rate-limit filter reading Redis counters. | Redis keys: auth:revoked:{jti} TTL=token-exp, rl:login:{ip} sliding window TTL, policy:rbac:{role} TTL=15m; DB remains source of truth; Riak unaffected for this control. | Immediate revocation capability, brute-force mitigation, reduced stale authorization decisions. | SOC2 CC6/CC7, ISO 27001 A.8/A.12, GDPR Art. 32
SOC2 Missing: Riak storage controls absent because Riak integration is absent | No object-storage strategy exists for immutable security/compliance artifacts (audit snapshots, DSAR archives, consent snapshots). | Introduce Riak adapter layer for append-only compliance artifacts with bucket types enforcing replication and conflict policies. | Create RiakClientConfig and RiakComplianceStore service; write through service APIs only (storeAuditSnapshot, storeExportArtifact); maintain repository abstraction to avoid controller-level storage calls. | Riak buckets: audit-archive, privacy-export, consent-snapshot; store encrypted payload + metadata (owner, purpose, retention_until); Redis caches object pointers for fast retrieval; DB stores index/reference records. | Durable immutable archival path, separation of operational DB from compliance evidence, and safer long-term artifact retention. | SOC2 CC8/CC9, ISO 27001 A.8/A.12, GDPR Art. 30/32
SOC2 Missing: Centralized monitoring/tracing instrumentation not implemented | Monitoring is mostly health endpoint + app logs; no standardized metrics, tracing, or alert-grade security telemetry emission. | Adopt Micrometer + Spring Boot Actuator metrics and structured security telemetry pipeline. Add security KPIs and incident-oriented events. | Config: expose metrics endpoint internally; Service/Filter: publish counters (auth_failures, token_revocations, access_denied); add HandlerInterceptor for latency/status tagging and correlation-id propagation. | Redis: optional rolling counters for near-real-time anomaly checks; Riak: store periodic immutable monitoring snapshots for audit evidence; DB: optional security_incidents table. | Faster detection of abuse/misconfiguration, measurable control effectiveness, and better forensic readiness. | SOC2 CC7 (monitoring), ISO 27001 A.12/A.16, GDPR Art. 32
ISO27001 Partial: Encryption practice is mixed (BCrypt good, AES utility weak) | Symmetric crypto utility uses hardcoded key and ECB mode, likely introduced as convenience without centralized crypto policy. | Replace with envelope encryption using AES-GCM (Cipher.getInstance("AES/GCM/NoPadding")) and key material from KMS/Vault. Standardize via CryptoService bean. | Service: CryptoService.encrypt/decrypt with random IV per record and auth tag; Config: inject active key id from env/secret manager; replace direct EncryptionUtil calls in auth/user services. | DB/Riak: store {keyId, iv, ciphertext, tag} per encrypted field/object; Redis: never store plaintext secrets; cache only encrypted blobs or opaque references with TTL. | Confidentiality + integrity protection, removal of static key exposure, and cryptographic agility via key ids. | ISO 27001 A.8/A.10, SOC2 CC6.6, GDPR Art. 32
ISO27001 Partial: Secure configuration has unsafe defaults (useSSL=false, ddl-auto=update) | Environment hardening boundaries are not enforced by profile-specific config governance and startup validation. | Implement secure-by-default profile policy with startup guard rails (@ConfigurationProperties + validator) that fail fast on unsafe production settings. | Config: SecurityBaselineProperties + @PostConstruct checks (if(prod && !dbSsl) throw); Security config: tighten actuator and CORS defaults; remove dangerous fallbacks from prod properties. | DB: enforce TLS connection parameters and cert validation; Redis/Riak clients configured with TLS and auth in production profiles. | Prevents insecure runtime drift, ensures encrypted transport to data stores, and blocks accidental weak deployments. | ISO 27001 A.5/A.8/A.12, SOC2 CC5/CC6, GDPR Art. 32
ISO27001 Partial: Risk controls are selective, not codified uniformly | Security controls are spread across ad-hoc checks and comments; no policy-as-code baseline across modules. | Create security control framework: baseline annotations, centralized validators, and CI policy checks for critical controls. | Add @SensitiveOperation + interceptor enforcing MFA freshness/role checks where required; add centralized SecurityPolicyService; add build-time checks (e.g., ArchUnit) enforcing controller/service security rules. | Redis: store control state (e.g., risk flags/session trust level) with TTL; Riak: archive periodic policy compliance snapshots. | Consistent risk treatment, fewer control gaps in new modules, and auditable enforcement semantics. | ISO 27001 A.5/A.6/A.12, SOC2 CC3/CC6/CC8
ISO27001 Missing: Secrets management pattern not compliant (secrets in properties) | Application reads static secrets from repo-managed property files instead of runtime secret sources. | Externalize all secrets to Vault/KMS/secret manager and inject via environment or Spring Cloud Vault; keep properties as placeholders only. | Config: replace literal secrets with ${...} references; add SecretProvider abstraction for JWT/DB/API keys; startup check rejects default/test secret values in non-dev profiles. | DB: rotate credentials and move to short-lived auth where possible; Redis/Riak credentials sourced from secret manager and rotated regularly. | Eliminates credential leakage from SCM, supports rotation, and reduces blast radius of compromised artifacts. | ISO 27001 A.5/A.8, SOC2 CC6.1/CC6.6, GDPR Art. 32
ISO27001 Missing: No key rotation/revocation lifecycle for JWT/API secrets | Single static key model is used; JWT validation does not support multi-key (kid) or revocation lifecycle. | Implement key management lifecycle: JWKS-style key ring, active/previous keys, scheduled rotation, and emergency revocation. | Security: add JwtKeyProvider supporting kid; token minting adds header kid; validation resolves key by kid; add admin/internal endpoint to mark keys revoked and trigger cache invalidation. | Redis: keys:active, keys:revoked:{kid} with TTL; DB: security_keys table (kid, status, created_at, revoked_at); Riak: immutable key-rotation audit records. | Supports seamless rotation, fast revocation after compromise, and reduced long-term key exposure risk. | ISO 27001 A.10/A.12, SOC2 CC6/CC7, GDPR Art. 32
ISO27001 Missing: No systematic field-level encryption for sensitive persisted data | PII is stored in plaintext in operational entities; encryption is not enforced by persistence layer policy. | Apply transparent field encryption with JPA AttributeConverter or service-level crypto wrappers for marked fields (@EncryptedField). | Entity/DAO: annotate sensitive fields (email/phone/address/tokens) and bind converters; Service: decrypt only at boundary where needed; add masking in DTO mappers for non-privileged responses. | DB: migrate existing plaintext to encrypted columns via controlled migration job; Redis: store only masked/minimal PII; Riak: encrypt object payload before write and maintain keyId metadata. | Data-at-rest hardening for PII, reduced impact from DB dumps, and stronger compartmentalization of sensitive values. | ISO 27001 A.8/A.10, SOC2 CC6.6, GDPR Art. 32
Cross-cutting Risk: Sensitive data appears in logs and exception messages | Controllers log request-associated values and concatenate raw exception messages into API responses; no centralized redaction policy. | Adopt structured logging with redaction filters and standardized error translation (@ControllerAdvice) returning sanitized error codes. | Logging: add MaskingPatternLayout/MDC redaction strategy; Web: global exception handler maps internal exceptions to safe payloads; remove direct logging of URLs/session IDs/PII fields in controllers. | Redis: optional temporary correlation-id map for incident tracing without storing raw payload; Riak: long-term audit logs store masked fields only. | Prevents PII/token leakage via logs/responses, improves incident handling without exposing sensitive context. | GDPR Art. 5(1)(f)/32, SOC2 CC6/CC7, ISO 27001 A.12
GDPR Missing: Personal data inventory and access registry is not centralized | Personal data usage is spread across DTOs/entities/services without a single inventory mapping data category, storage location, access scope, and processor context. | Implement a Data Inventory Registry module that maps personal/sensitive data fields to source endpoints, storage systems, retention period, and authorized roles; keep registry queryable for audits. | Add DataInventoryController (internal/compliance), DataInventoryService, and metadata scanners for DTO/entity annotations; add role-restricted endpoints to view inventory and access map. | DB: data_inventory_catalog table with fields for data_type, sensitivity, purpose, storage_system, retention_rule, access_roles, processor_reference; Redis optional cache for lookup. | Improves accountability, least-privilege reviews, and rapid impact analysis during incidents or data-subject requests. | GDPR accountability/Art. 30 readiness, SOC2 CC3/CC6, ISO 27001 A.5/A.8
GDPR Missing: Minors (under 16) consent and age-gating controls are not implemented | Registration/data collection flows do not model age verification or parental authorization conditions. | Add age-threshold validation and parental consent workflow for minors, including status transitions and verification evidence retention. | Update relevant registration/profile DTOs and controllers with age fields/flags; add MinorConsentService and guard checks before processing optional personal data. | DB: user_age_verification and parental_consent_records tables; Redis for pending verification/session TTL. | Reduces unlawful processing risk for minors and enforces stricter controls over sensitive user segments. | GDPR Art. 8 (children consent), SOC2 CC6, ISO 27001 A.8
GDPR Missing: Cookie and form consent lifecycle controls are not comprehensively implemented | Consent capture is not standardized for cookie categories, form privacy notices, correspondence opt-in, and consent withdrawal history. | Implement Consent Preference Center backend APIs for cookie categories, form consent proof, correspondence preferences, and withdrawal/change history. | Add ConsentPreferenceController and FormConsentService; enforce consent checks in data-collection endpoints and messaging workflows. | DB: consent_preferences, form_consent_events, correspondence_preferences; Redis for active consent cache with durable DB source. | Creates auditable proof of consent state and persistent opt-out enforcement. | GDPR consent transparency/opt-in expectations, SOC2 CC7/CC8, ISO 27001 A.12
GDPR Missing: Third-party processor and international transfer governance is not modeled | Backend compliance artifacts do not maintain processor catalog, transfer basis, safeguards, or review status. | Add Processor Governance module to register third-party processors, transfer regions, legal basis, DPA status, and transfer safeguards. | Add ProcessorController and TransferGovernanceService with policy validation hooks for integrations that handle personal data. | DB: processors, processor_assessments, transfer_mechanisms, transfer_risk_reviews tables; optional Riak archival of signed assessment documents. | Strengthens vendor oversight and cross-border transfer accountability. | GDPR Chapter V transfer governance, SOC2 CC3/CC9, ISO 27001 supplier relationship controls
GDPR Missing: Breach response and 72-hour notification workflow is not implemented | No structured incident workflow exists for breach classification, authority notification timelines, affected-user communication, and corrective action tracking. | Implement Breach Response Orchestration module with incident states, timer-based SLA checks, notification templates, and evidence bundle generation. | Add BreachIncidentController and BreachResponseService; integrate security event triggers and escalation hooks. | DB: breach_incidents, breach_notifications, breach_actions, breach_impacted_subjects tables; Redis timer queues for SLA reminders. | Improves regulatory response readiness and repeatable incident handling. | GDPR Art. 33/34, SOC2 CC7/CC8, ISO 27001 incident management controls
Legend
Issue Row | One remediation design per issue

## Estimation
Issue | Tasks (comma separated) | Effort (S/M/L/XL) | Complexity Reason | Impacted Components | Dependencies | Parallelizable (Yes/No)
GDPR Partial: Data portability only covers course/package exports, not subject-level personal data export | Design `PersonalDataExportDto` contract and export schema (JSON + optional CSV bundle), Build `DataPortabilityController` and async export job APIs, Implement `DataPortabilityService` with fan-out across user/billing/auth/usage repositories, Add export job persistence, status polling, and signed download URL flow, Add audit events for request/start/complete/download actions, Add integration tests for ownership, payload completeness, and expiry behavior | L | Cross-domain data aggregation and async orchestration are required; backward compatibility must be preserved while introducing new privacy APIs and download workflow. | Controller, Service, DAO, Redis, Riak, Security Config | Export artifact storage decision (DB filesystem vs Riak), Token/signing strategy for download links, Infra capacity for large export generation | Yes
GDPR Partial: Data minimization is inconsistent across DTOs | Inventory current DTOs and classify fields by legal/business necessity, Create purpose-scoped DTO variants and validation groups, Implement `DataMinimizationPolicyService` for endpoint-role field allowlists, Harden JSON binding for sensitive endpoints (reject unknown/excess fields), Refactor affected controllers/services to new DTO contracts, Add regression tests for over-posting and blocked fields | L | High controller/service touch points and high regression risk due to request-contract changes across many endpoints. | Controller, Service, DAO, Security Config | Product/legal sign-off on minimum data set per endpoint, API contract compatibility plan for existing clients | Yes
GDPR Partial: Purpose limitation is implicit, not explicit/enforced | Define `ProcessingPurpose` enum and purpose-policy matrix, Implement `@RequiresPurpose` annotation and AOP enforcement, Propagate processing context from controller to service methods, Add audit metadata (`purpose`, `legal_basis`) to trail records, Add policy caching and invalidation flow | L | Requires cross-cutting pattern changes and method signature updates in service layer; impacts many existing flows. | Controller, Service, DAO, Redis, Riak, Security Config | Policy ownership model (who defines and updates purpose matrix), Coordination with audit logging model | Yes
GDPR Missing: Consent tracking ledger/versioning not implemented | Design consent domain model (`user_consents`, `consent_events`), Implement `ConsentController` for capture/read/withdraw endpoints, Implement append-only consent event write path with integrity hash, Add consent state cache for runtime policy checks, Integrate consent checks into optional-data processing services, Add test coverage for versioning and consent withdrawal semantics | L | New privacy subsystem with write-once event semantics and downstream integration into existing business actions. | Controller, Service, DAO, Redis, Riak, Security Config | Legal policy versioning conventions, Event immutability approach and archival requirement | Yes
GDPR Missing: Comprehensive subject-access endpoint not implemented | Define DSAR response model (machine-readable + human-readable export), Create `DataSubjectAccessController` and DSAR request workflow, Implement `DsarAggregationService` with repository projections, Add throttling, idempotency, and async fulfillment status APIs, Persist DSAR request lifecycle and fulfillment audit records, Add e2e tests for access boundaries and anti-replay controls | L | Broad aggregation and strict access assurance needed; similar complexity to portability with additional SLA/state tracking. | Controller, Service, DAO, Redis, Riak, Security Config | Shared data model decisions with portability module, Operational SLA and queueing strategy | Yes
GDPR Missing: Centralized retention/deletion policy engine for PII | Define retention policy model and rule schema, Implement `RetentionEngineService` with scheduled execution and dry-run mode, Add entity-specific deletion/anonymization handlers, Add execution logs, error dead-letter handling, and rerun support, Implement distributed lock/checkpointing for singleton scheduler, Backfill policy coverage tests for major PII entities | XL | Cross-entity destructive processing with high data-loss risk, strong idempotency requirements, and operational rollback concerns. | Service, DAO, Redis, Riak, Security Config | Data ownership map across all PII tables/entities, Operational approval workflow for deletion policies, Backup/restore validation before rollout | No
SOC2 Partial: Access control split between permitAll filter chain and custom interceptor/manual checks | Refactor `SecurityFilterChain` to deny-by-default and explicit public allowlist, Implement `JwtAuthenticationFilter` (`OncePerRequestFilter`) and populate `SecurityContext`, Add centralized auth error handling (`AuthenticationEntryPoint`, `AccessDeniedHandler`), Remove manual bearer parsing from controllers/services, Migrate existing interceptor-only checks to Spring Security primitives, Run endpoint-by-endpoint regression security tests | L | High blast radius authentication change; every endpoint behavior (401/403/public) must be revalidated. | Controller, Service, Security Config, Redis, DAO | Complete public endpoint inventory, Coordination with RBAC standardization item | No
SOC2 Partial: RBAC exists but is uneven and not centralized | Enable method security globally and define authorization conventions, Implement custom `PermissionEvaluator` and workspace-scoped checks, Replace manual role checks with `@PreAuthorize` across critical methods, Normalize role-permission model and repository access patterns, Add permission-cache invalidation strategy and tests | L | Touches many service/controller methods and requires careful compatibility with existing role semantics. | Controller, Service, DAO, Redis, Security Config | Depends on access-control refactor baseline, Role model cleanup and data seeding strategy | No
SOC2 Partial: Audit logging coverage is limited to selected actions | Define critical action catalog and audit schema, Implement `@Auditable` annotation and AOP capture layer, Create async `AuditWriter` with structured JSON and correlation IDs, Persist audit records to DB and optional immutable archive, Instrument auth/privilege/data-change flows, Add tamper-evidence/hash-chain verification tests | L | Cross-cutting instrumentation with performance sensitivity and schema design requirements for long-term storage. | Controller, Service, DAO, Redis, Riak, Security Config | Final action taxonomy from security/compliance, Storage sizing and retention policy alignment | Yes
SOC2 Missing: Redis caching controls absent because Redis integration is absent | Add Spring Data Redis dependency and `RedisConfig`, Implement token revocation cache (`jti`) and logout invalidation, Implement login/API rate-limiting filter backed by Redis counters, Add policy/permission cache namespaces and TTL standards, Add resilience/fallback behavior when Redis is unavailable, Add integration tests against Redis test container | M | Net-new infra integration but bounded scope if limited to revocation/rate-limit/policy cache primitives. | Service, Redis, Security Config, Controller | Redis instance provisioning and network/security setup, Operational monitoring for cache availability | Yes
SOC2 Missing: Riak storage controls absent because Riak integration is absent | Introduce Riak client configuration and health integration, Implement `RiakComplianceStore` abstraction and bucket conventions, Build write/read adapters for audit/privacy artifacts, Add metadata model (owner, purpose, retention, checksum), Integrate encryption before Riak write path, Add failure/retry and archive retrieval tests | L | Greenfield NoSQL integration with serialization, metadata, and reliability concerns; requires operational readiness. | Service, DAO, Riak, Redis, Security Config | Riak cluster availability and bucket policy setup, Crypto/key management dependency for encrypted payloads | Yes
SOC2 Missing: Centralized monitoring/tracing instrumentation not implemented | Enable Micrometer metrics and structured telemetry baseline, Instrument auth/security counters and API latency/status metrics, Add correlation-id propagation interceptor/filter, Define alertable SLO/SLI metrics and tags, Add dashboards/alerts hooks for security events, Add load tests to validate overhead | M | Implementation is straightforward but requires alignment with runtime observability stack and naming conventions. | Controller, Service, Security Config, Redis, Riak | Monitoring backend availability (Prometheus/APM/SIEM), Alert routing ownership | Yes
ISO27001 Partial: Encryption practice is mixed (BCrypt good, AES utility weak) | Design `CryptoService` with AES-GCM envelope format, Integrate key-id aware encryption/decryption APIs, Replace legacy `EncryptionUtil` usages in auth/user flows, Add cryptographic test vectors and backward compatibility migration strategy, Add key rotation support hooks in crypto layer | L | Security-critical refactor with backward compatibility constraints for previously encrypted values. | Service, DAO, Security Config, Riak, Redis | Secret management/KMS availability, Data migration plan for old encrypted payloads | No
ISO27001 Partial: Secure configuration has unsafe defaults (useSSL=false, ddl-auto=update) | Create secure baseline config validator and fail-fast startup checks, Harden prod properties (DB TLS, actuator, CORS, SQL logging levels), Add profile-specific configuration tests, Document and enforce non-dev forbidden config values | S | Mostly configuration and guardrail logic with limited code churn. | Security Config, DAO, Redis, Riak | Infra cert setup for DB/Redis/Riak TLS, Deployment pipeline update for secure env vars | Yes
ISO27001 Partial: Risk controls are selective, not codified uniformly | Define security control baseline and annotation model (`@SensitiveOperation`), Implement enforcement interceptor/policy service, Add CI architecture/security policy checks (e.g., ArchUnit rules), Refactor high-risk endpoints/services to baseline controls, Add control conformance reporting | L | Framework-level changes plus broad adoption effort across existing modules. | Controller, Service, Security Config, Redis, Riak | Security governance ownership for policy definitions, Team adoption and code-review checklist updates | Yes
ISO27001 Missing: Secrets management pattern not compliant (secrets in properties) | Replace hardcoded properties with env/secret references, Implement `SecretProvider` abstraction and startup validation, Integrate Vault/KMS/secret manager client for runtime retrieval, Rotate exposed credentials and invalidate old secrets, Update deployment manifests/pipelines for secret injection | L | App and infra changes are tightly coupled; credential rotation must be coordinated with zero downtime. | Security Config, Service, DAO, Redis, Riak | Secret manager provisioning and IAM policies, Credential rotation windows with external providers (DB, SMTP, Stripe, etc.) | No
ISO27001 Missing: No key rotation/revocation lifecycle for JWT/API secrets | Design key registry model (`kid`, status, activation, revocation timestamps), Implement `JwtKeyProvider` supporting active/previous keys, Add token minting with `kid` and validation by key id, Implement admin/internal key revoke/rollover workflow, Add cache invalidation and propagation for revocation events, Add rotation runbook and automated rotation tests | L | Authentication core behavior changes and requires safe rollout for existing active tokens. | Security Config, Service, DAO, Redis, Riak, Controller | Depends on secrets/KMS integration, Client/session compatibility strategy during cutover | No
ISO27001 Missing: No systematic field-level encryption for sensitive persisted data | Identify sensitive fields across entities and repositories, Implement JPA `AttributeConverter` or encrypted-field abstraction, Apply encryption/decryption to entity persistence path, Build migration job to re-encrypt existing plaintext data, Update query/index strategy for encrypted fields, Add masking in DTO mappers and privileged-read checks | XL | Large data-model impact, migration complexity, query behavior changes, and high backward compatibility risk. | DAO, Service, Controller, Security Config, Redis, Riak | Crypto service and key lifecycle readiness, Data migration window and rollback strategy, Performance validation for encrypted fields | No
Cross-cutting Risk: Sensitive data appears in logs and exception messages | Define log redaction policy (PII/token/session patterns), Implement centralized redaction/masking in logging pipeline, Add global exception translator with sanitized API error model, Refactor controllers to remove raw payload/exception message logging, Add tests for redaction and safe error responses | M | Cross-cutting but technically straightforward; main effort is endpoint cleanup and regression validation. | Controller, Service, Security Config, Riak, Redis | Agreement on masking rules and observability format, Coordination with audit logging implementation | Yes
GDPR Missing: Personal data inventory and access registry is not centralized | Define inventory schema and ownership model, Implement inventory APIs and service, Tag DTO/entity fields by data class/sensitivity, Build storage/access mapping views, Add governance reports and tests | L | Cross-cutting metadata capture across many modules with governance validation dependency. | Controller, Service, DAO, Security Config | Compliance owner approval for taxonomy, Data classification policy finalization | Yes
GDPR Missing: Minors (under 16) consent and age-gating controls are not implemented | Add age verification fields/validation, Implement parental consent workflow, Block processing without valid consent state, Add audit trail and expiry handling, Add integration/regression tests | L | Changes user onboarding and consent states with legal-policy sensitivity and compatibility impact. | Controller, Service, DAO, Security Config, Redis | Legal policy for age verification, UX/frontend flow alignment | No
GDPR Missing: Cookie and form consent lifecycle controls are not comprehensively implemented | Implement consent preference APIs, Capture form-level consent evidence, Add opt-in/opt-out/withdraw endpoints, Integrate consent checks into messaging/forms, Add consent reporting and tests | L | Requires coordination with frontend behavior and persistent consent history enforcement. | Controller, Service, DAO, Redis, Security Config | Frontend cookie/banner implementation alignment, Policy text/version governance | Yes
GDPR Missing: Third-party processor and international transfer governance is not modeled | Create processor and transfer schema, Build processor registry APIs, Capture transfer safeguards and assessments, Link processors to data flows, Add periodic review workflow | M | Mostly governance data modeling with lower runtime risk but depends on policy inputs. | Controller, Service, DAO | Legal/compliance input for transfer basis, Vendor inventory completeness | Yes
GDPR Missing: Breach response and 72-hour notification workflow is not implemented | Design incident state machine, Implement breach incident APIs, Add timer-based 72-hour escalation logic, Build authority/user notification tracking, Create post-incident action records | L | Workflow orchestration and SLA-driven operations require reliable state transitions and alerting. | Controller, Service, DAO, Redis, Security Config | SOC/incident-management process integration, Notification channel ownership | No
Legend
S | Small effort (1-2 days)
M | Medium effort (3-5 days)
L | Large effort (1-2 weeks)
XL | Extra large effort (2+ weeks)
Yes | Can run in parallel
No | Not parallelizable / critical dependency

## Executive Summary
Category | Details
Total Issues Count | 40
Missing Controls Count | 17
High Risk Areas | Hardcoded secrets and credentials in config files (spring.datasource.password, jwt.secret, OpenAI keys, SMTP password, ZeptoMail key, Stripe keys) create credential exposure and compromise risk. ¦ Authorization model risk: SecurityConfig permits all requests at filter-chain level, with enforcement moved to custom interceptor/manual checks, increasing bypass/misconfiguration risk. ¦ Potential sensitive-data logging risk: request-associated values (e.g., imageUrl, sessionId, search criteria) and exception message propagation appear in controller logging/response paths. ¦ Cryptographic weakness risk from EncryptionUtil hardcoded AES key and AES/ECB/PKCS5Padding usage. ¦ Data subject rights coverage risk: deletion exists for user path, but comprehensive personal-data portability and consent lifecycle evidence is not present. ¦ Assurance gap risk for cache/NoSQL controls because Redis/Riak control implementation is absent in code. ¦ GDPR governance risk: missing centralized processor/international transfer controls can expose the organization to cross-border compliance violations. ¦ Consent evidence risk: absence of structured cookie/form/privacy-policy consent logs may weaken legal defensibility during audits or complaints. ¦ Incident response risk: without breach workflow orchestration and notification tracking, 72-hour GDPR notification obligations may be missed.
Quick Wins (Small effort items) | ISO27001 Partial: Secure configuration has unsafe defaults (useSSL=false, ddl-auto=update)
Critical Path Items | SOC2 Partial: Access control split between permitAll filter chain and custom interceptor/manual checks ¦ SOC2 Partial: RBAC exists but is uneven and not centralized ¦ ISO27001 Missing: Secrets management pattern not compliant (secrets in properties) ¦ ISO27001 Missing: No key rotation/revocation lifecycle for JWT/API secrets ¦ ISO27001 Partial: Encryption practice is mixed (BCrypt good, AES utility weak) ¦ ISO27001 Missing: No systematic field-level encryption for sensitive persisted data ¦ GDPR Missing: Centralized retention/deletion policy engine for PII ¦ GDPR Missing: Minors (under 16) consent and age-gating controls are not implemented ¦ GDPR Missing: Breach response and 72-hour notification workflow is not implemented
Overall Maturity | Low
Estimated Timeline | Single-team sequential: ~28-36 weeks. With 3 parallel streams (Security Core, Privacy/Data Rights, Platform/Observability): ~14-18 weeks including integration hardening.
Legend
High Maturity | Stronger control coverage
Medium Maturity | Mixed control maturity
Low Maturity | Significant gaps remain